## Sheet1
GODOT-CHESS
Number	Status	Priority	Name	Deliverable	Description	Planned			Actual		Key Players	Notes
					Start	End	Days Left	Start	End
1	Done	High	Plan the project	Detailed project tracker	Do your Work Breakdown Structure / first, this tracker later	11/02/22	21/02/22	10	06/02/22	08/02/22	Ki, Chi	Copy paste this line down to keep the formulas
CORE

1	Pending	Low	Player					???				Copy paste this line down to keep the formulas
2	Pending	Low	Human					???				Copy paste this line down to keep the formulas
3	Pending	Low	Engine					???				Copy paste this line down to keep the formulas
2	Pending	Low	Judge					???				Copy paste this line down to keep the formulas
3	Done	Low	Move					???	09/02/22	09/02/22		Copy paste this line down to keep the formulas
4	Done	Low	Action					???	09/02/22	09/02/22		Copy paste this line down to keep the formulas
5	Done	Low	Mobilize					???	11/02/22	11/02/22		Copy paste this line down to keep the formulas
6	Done	Low	Capture					???	11/02/22	11/02/22		Copy paste this line down to keep the formulas
7	Done	Low	Spawn					???	11/02/22	11/02/22		Copy paste this line down to keep the formulas
8	Running	Low	Piece	All Piece Types				???	09/02/22			Copy paste this line down to keep the formulas
9	Running	Low	Board					???	09/02/22			Copy paste this line down to keep the formulas

EXTENSION